## 4
RTF 4 FYs 2017-2020
2017-12-21
Required Fields | [24 empty] | Optional Fields
Fiscal Year | County | Responsible Agency | Project Name | Limits | Length | Primary Work Type | Project Description | Phase | Advance Construct | Federal Cost | Federal Fund Source | State Cost | State Fund Source | Local Cost | Local Fund Source | Total Phase Cost | MDOT Job No. | Local ID No. | Rural Action Date | Amend-ment Type | Air Quality | Comments | Total Project Cost | x | Local Priority | EJ | Approval Date | Capped Federal Cost ($1000s) | Date Obligated | Amount Obligated ($1000s) | Let Date | RTF
2017 | Berrien | Berrien County Road Commission | Red Arrow Highway | City of Bridgman limits to 0.8 miles South | 0.8 | Resurface | 3R Project | CON |  |  | STL |  | M |  |  |  | 127134 |  | 2016-01-20 |  | Exempt | 1/20/16- RTF 4 Approved Deleted and moved to illustrative list May 26, 2016 | 0 |  |  |  | 2016-02-11 |  |  |  |  | 4
2017 | Berrien | Berrien County Road Commission | Territorial Road | North Branch Road to Millburg Drive | 0 | Bridge replacement | Territorial Road Culvert Replacement | CON | AC | 709167 | STL | 0 |  | 329548 | CNTY | 1038715 | 131453 |  | 2017-02-13 | Add | Exempt | 2/13/17 Admin Mod: Partial AC of $121,805 to be converted in 2018. local cost if $207,843. 10/7/2016 Added to Budget. | 1038715 |  |  |  | 2017-02-15 |  |  |  |  | 4
2017 | Berrien | Berrien County Road Commission | Hills Road | Village of Baroda limits to Shawnee Road |  | Resurface | Hills Road Resurface | CON |  |  | STL |  | M |  | CNTY |  |  |  | 2016-10-07 | Delete |  | 10/7/2016 - moved to illustrative list. 5/26/16 RTF 4 Approval |  |  |  |  | 2016-10-12
2017 | Cass | Cass County Public Transit | Property Acquisition for Transit Facility | Village of Cassopolis at 408 E State St. | 0 | Transit facility | Purchase building at 408 E State St , to allow space for Cass County transit vehicles to park. This facility is adjacent to the current county transit facility | T-Cap |  | 72000 | STL |  |  | 18000 | TRAL | 90000 | 129833 |  | 2016-01-20 |  | Exempt | 1/20/16- RTF 4 Approved | 90000 |  |  |  | 2016-02-11 |  |  |  |  | 4
2017 | Cass | Cass County Road Commission | Calvin Center Rd | Grange to Mason | 0.75 | Resurface | Resurface | CON |  |  | STL |  | M |  |  |  | 120103 |  | 2016-01-20 | Year | Exempt | 1/20/16- RTF 4 Approved Moved to 2016 March 18 2016 |  |  |  |  | 2016-02-11 |  |  |  |  | 4
2017 | Cass | Cass County Road Commission | Pavement Marking | Pavement marking | 0 | Traffic ops/safety | Pavement Marking centerline and edgeline on selected roads | CON |  | 158380 | STL |  |  |  | CNTY | 158380 | 124369 |  | 2017-03-13 | Cost | Exempt | 1/20/16- RTF 4 Approved | 158380 |  |  |  | 2016-12-01 |  |  |  |  | 4
2017 | Cass | Cass County Road Commission | Dailey Rd | Peavine to Mathews | 0.55 | Resurface | 1-1/2 inch HMA overlay with aggregate shoulders | CON |  | 52111 | STL | 13028 | M |  |  | 65139 | 120113 |  | 2017-03-13 | Cost | Exempt | 1/20/16- RTF 4 Approved | 65139 |  |  |  | 2016-12-01 |  |  |  |  | 4
2017 | Cass | Cass County Road Commission | Redfield Rd | Township Line - Cassopolis | 0.872 | Resurface | Resurface | CON |  | 65270 | STL | 16318 | M | 0 |  | 81588 | 120116 |  | 2017-03-13 | Cost | Exempt | 1/20/16- RTF 4 Approved | 84600 |  |  |  | 2016-02-11 |  |  |  |  | 4
2017 | Cass | Cass County Road Commission | Redfield Rd | Conrad - M-62 | 1 | Resurface | Resurface | CON |  |  | STL |  | M |  |  |  | 120117 |  | 2017-03-13 | Delete | Exempt | 3/13/17 Deleated 1/20/16- RTF 4 Approved | 93600 |  |  |  | 2016-02-11 |  |  |  |  | 4
2017 | Cass | Cass County Road Commission | Fir Road | Redfield o US 12 | 1.023 | Resurface | 1-1/2 inch HMA overlay with aggregate shoulders | CON |  | 74933 | STL | 18733 | M |  | CNTY | 93666 | 133108 |  | 2016-11-21 | Add | Exempt | Added to TIP 11/21/16 | 93666 |  |  |  | 2016-12-01 |  |  |  |  | 4
2017 | Cass | Cass County Road Commission | Pokagon Highway | Hampshire to Anderson | 1 | Resurface | Resurface | CON |  | 74407 | STL | 18602 | M |  |  | 93009 | 129842 |  | 2017-03-13 |  | Exempt | 1/20/16- RTF approved | 93009 |  |  |  | 2016-02-11 |  |  |  |  | 4
2017 | Cass | Cass County Road Commission | Decatur Road | Crane-Brewer | 2.5 | Restore & rehabilitate | Mill and fill and overlay | CON | ACC | 24509 | STL |  |  |  |  | 24509 | 123749 |  | 2016-11-21 |  | Exempt | This is the Last ACC for this project. The project s now balanced out | 24509 |  |  |  | 2016-12-01 |  |  |  |  | 4
2017 | Cass | Village of Cassopolis | N. O'Keefe St | State Street to York | 0.124 | Resurface | Resurface | CON |  | 38800 | STL |  |  | 9500 | VLG | 48300 | 123748 |  | 2016-11-21 | Scope | Exempt | 11/21/16 remove South Street from this prject. Reduced costs accordingly. Now completely STP funded 1/20/16- RTF 4 Approved | 42200 |  |  |  | 2016-12-01 |  |  |  |  | 4
2017 | Cass | Village of Cassopolis | South Street | S. O'keefe St to East St. | 0.128 | Resurface | Resurface | CON |  |  |  | 31700 | M | 7925 | VLG | 39625 | 133106 |  | 2016-11-21 | Add | Exempt | Added to TIP 11/21/16 | 31700 |  |  |  | 2016-12-01 |  |  |  |  | 4
2017 | Van Buren | City of Bangor | South Center Street | Arlington St - South City Limits, Bangor | 0.305 | Resurface | Resurface | CON |  | 100000 | STL |  |  | 25000 | CITY | 125000 | 116597 |  | 2016-01-20 |  | Exempt | 1/20/16- RTF Approved. Increased federal and local costs | 125000 |  |  |  | 2016-02-11 |  |  |  |  | 4
2017 | Van Buren | Van Buren County Road Commission | CR 687 | I94 - CR 352 | 5.5 | Resurface | Trench and widen shoulders, mill and overlay existing section, adjust/upgrade guardrail as required, drainage improvements and all associated work. | CON | AC | 553030 | STL |  |  | 478530 | CNTY | 1031560 | 123771 |  | 2016-11-21 |  | Exempt | Partial AC to FY 2018 for $272,218. Local match of $206,312 after ACC. Project is being done inc onjnction with a TAP project using TAP funds of $402484 and a match of $268,322. 1//20/2016- RTF Approved | 1031560 |  |  |  | 2017-02-15 |  |  |  |  | 4
2017 | Van Buren | Van Buren Public Transit | Area Wide Transit | Van Buren Public Transit, Bangor, Van Buren County | 0 | Transit vehicle additions/replacements | Bus Purchase | CON |  | 104000 | STL |  |  | 26000 | TRAL | 130000 | 119995 |  | 2016-01-20 |  | Exempt | 1/2016- RTF Approved Increased federal and local costs | 130000 |  |  |  | 2016-02-11 |  |  |  |  | 4
2017 | Van Buren | Village of Bloomingdale | Kalamazoo Street | Oak Street to East Village Limits | 0.56 | Reconstruct | Reconstruct | CON | ACC |  |  | 27852 | M |  |  | 27852 | 127133 |  | 2016-01-20 |  | Exempt | 1/20/16- RTF Approved | 407000 |  |  |  | 2016-02-11 |  |  |  |  | 4
2018 | Berrien | Berrien County Public Transit | Vehicle Cameras | New Cameras for transit vehicles | 0 | Transit operations equipment | Purchase new cameras for Berrien County transit vehicles. |  |  | 50000 | STL |  |  | 12500 | TRAL | 62500 | 129845 |  | 2016-01-20 |  | Exempt | 1/20/16- RTF approved | 62500 |  |  |  | 2016-02-11 |  |  |  |  | 4
2018 | Berrien | Berrien County Road Commission | Territorial Road | Territorial Road Culvert Project | 0 | Reconstruct | Territorial Road Culvert Replacement | CON | ACC | 121805 | STL | 0 |  |  |  | 121805 | 131453 |  | 2017-02-13 | Add | Exempt | 2/13/17 Admin Mod to increase cost 10/7/2016 Added to Budget. Repayment for AC in 2017. | 1038715 |  |  |  | 2016-10-12 |  |  |  |  | 4
2018 | Berrien | Berrien County Road Commission | Red Arrow Highway | Bridgman Village limits 0.8 mi south | 0.8 | Resurface | 3R Project | CON |  | 449334 | STL | 258769 | M | 0 |  | 708103 | 129834 |  | 2017-02-13 | Cost | Exempt | 2/13/17 Admin Mod to change costs & funding sources. 10/7/2016 - Limits and costs for Red Arrow were reprogramed. Starting from the Bridgman limits the county plans to work south at 0.8 miles per year. 1/12/16- RTF approved | 708103 |  |  |  | 2017-02-15 |  |  |  |  | 4
2018 | Cass | Cass County Road Commission | Pavement Marking | Pavement marking | 0 | Traffic ops/safety | Pavement Marking centerline and edgeline on selected roads | CON |  | 75000 | STL |  |  |  |  | 75000 | 129839 |  | 2016-01-20 |  | Exempt | 1/20/16- RTF 4 Approved | 75000 |  |  |  | 2016-02-11 |  |  |  |  | 4
2018 | Cass | Cass County Road Commission | Dutch Settlement Road | White Temple to Goff | 0.89 | Resurface | Resurface | CON |  | 75200 | STL | 18800 | M |  |  | 94000 | 129843 |  | 2016-01-20 |  | Exempt | 1/20/16- RTF approved | 93600 |  |  |  | 2016-02-11 |  |  |  |  | 4
2018 | Cass | Cass County Road Commission | Cassopolis Road | Lost to Bullhand | 0.7 | Resurface | Resurface | CON |  | 75200 | STL | 18800 | M |  |  | 94000 | 129844 |  | 2016-01-20 |  | Exempt | 1/20/16- RTF approved | 93600 |  |  |  | 2016-02-11 |  |  |  |  | 4
2018 | Cass | Cass County Transportation Authority | Transit | Transit | 0 | Transit operations equipment | Dispatch hardware and software purchases | T-Ops | [8 empty] | 123773 |  | 2016-11-21 | Delete | Exempt | Reporting rules require spliting this proejct into sperate projects with more detailed itemization of costs. 1/20/16- RTF approved | 30000 |  |  |  | 2016-12-01 |  |  |  |  | 4
2018 | Cass | Cass County Transportation Authority | Office Equiptment | Village of Cassopolis at 408 E State St. | 0 | Transit operations equipment | One coppier | T-Ops |  | 2000 | STL |  |  | 500 | TRAL | 2500 | 133113 |  | 2016-11-21 |  |  | Reporting rules require spliting the facilities proejct into sperate projects with more detailed itemization of costs. | 2500 |  |  |  | 2016-12-01
2018 | Cass | Cass County Transportation Authority | Facility Improvments | Village of Cassopolis at 408 E State St. | 0 | Transit operations equipment | Office and garage building improvemnts | T-Ops |  | 15200 | STL |  |  | 3800 | TRAL | 19000 | 133114 |  | 2016-11-21 |  |  | Reporting rules require spliting the facilities proejct into sperate projects with more detailed itemization of costs. | 19000 |  |  |  | 2016-12-01
2018 | Cass | Cass County Transportation Authority | Computer Equiptment | Village of Cassopolis at 408 E State St. | 0 | Transit operations equipment | Three computers | T-Ops |  | 5200 | STL |  |  | 1300 | TRAL | 6500 | 133115 |  | 2016-11-21 |  |  | Reporting rules require spliting the facilities proejct into sperate projects with more detailed itemization of costs. | 6500 |  |  |  | 2016-12-01
2018 | Cass | Cass County Transportation Authority | Maintenance Equiptent | Village of Cassopolis at 408 E State St. | 0 | Transit operations equipment | Tool box & refrigerant recovery, recycling,& recharging machine | T-Ops |  | 5600 | STL |  |  | 1400 | TRAL | 7000 | 133116 |  | 2016-11-21 |  |  | Reporting rules require spliting the facilities proejct into sperate projects with more detailed itemization of costs. | 7000 |  |  |  | 2016-12-01
2018 | Cass | Village of Cassopolis | N. O'Keefe St | York to Hilton | 0.428 | Resurface | Resurface and install ADA ramps at sidewalk intersections | CON |  | 120000 | STL | 10000 | M | 20000 | VLG | 150000 | 129841 |  | 2016-11-21 | Scope | Exempt | Limits changed because original limits were not a federal aid eligible. 1/20/16-RTF Approved | 150000 |  |  |  | 2016-12-01
2018 | Van Buren | Van Buren County Road Commission | CR 687 | I94 - CR 352 | 5.5 | Resurface | Trench and widen shoulders, mill and overlay existing section, adjust/upgrade guardrail as required, drainage improvements and all associated work. | CON | ACC | 272218 | STL |  |  |  |  | 272218 | 123771 |  | 2016-11-21 |  | Exempt | 2/13/17 Admin Mod ACC for Construction in 2017. 11/21/16 changed to reflect removal of AC for State D funds 1/2016- RTF Approved; Coordinated with TAP grant in the area and TEDF funds; added Advance Construct Convert phase to allow for fiscal constraint in 2017 | 1031560 |  |  |  | 2017-02-15 |  |  |  |  | 4
2018 | Van Buren | Village of Lawrence | W St. Joseph St | S Paw Paw St to West Village Limits | 0.76 | Resurface | 13 | CON |  | 376100 | STL | 47013 | M | 47013 | VLG | 470126 | 129846 |  | 2017-01-05 |  |  | 1/5/17 - Admninstrative Mod to removed AC of state D funds. | 517138 |  |  |  | 2016-02-11 |  |  |  |  | 4
2019 | Berrien | Berrien County Road Commission | Red Arrow Highway | 0.8 miles south of the City limits of Bridgman to 1.6 miles South of the City of Bridgman | 0.8 | Resurface | 3R Project | CON |  | 400762 | STL | 117363 | M |  |  | 518125 | 129835 |  | 2015-10-07 | Cost | Exempt | 10/7/2016 - Cost and scope has been changed 1/12/16- RTF approved | 518125 |  |  |  | 2016-10-12 |  |  |  |  | 4
2019 | Berrien | Village of Baroda | Lemon Creek Road | First Street - Ruggles | 1 | Resurface | Resurface | CON |  | 232800 | STL |  |  | 56800 | VLG | 289600 | 120015 |  | 2016-01-20 |  | Exempt | 1/12/16- RTF approved | 289600 |  |  |  | 2016-02-11 |  |  |  |  | 4
2019 | Cass | Cass County Road Commission | Pavement Marking | Pavement marking | 0 | Traffic ops/safety | Pavement Marking centerline and edgeline on selected roads | CON |  | 75000 | STL |  |  |  |  | 75000 | 129847 |  | 2016-01-20 |  | Exempt | 1/12/16- RTF 4 Approved | 75000 |  |  |  | 2016-02-11 |  |  |  |  | 4
2019 | Cass | Cass County Road Commission | Pokagon Highway | Anderson to Wilbur Hill | 1 | Resurface | Resurface | CON |  | 75200 | STL | 18800 | M |  |  | 94000 | 129848 |  | 2016-01-20 |  | Exempt | 1/12/16- RTF approved | 93600 |  |  |  | 2016-02-11 |  |  |  |  | 4
2019 | Cass | Cass County Road Commission | Calvin Center Road | Bonine to M60 | 0.5 | Resurface | Resurface | CON |  | 52640 | STL | 13160 | M |  |  | 65800 | 129849 |  | 2016-01-20 |  | Exempt | 1/12/16- RTF approved | 65800 |  |  |  | 2016-02-11 |  |  |  |  | 4
2019 | Cass | Cass County Road Commission | Cassopolis Road | Mason to Lost | 0.8 | Resurface | Resurface | CON |  | 75200 | STL | 18800 | M |  |  | 94000 | 129851 |  | 2016-01-20 |  | Exempt | 1/12/16- RTF approved | 93600 |  |  |  | 2016-02-11 |  |  |  |  | 4
2019 | Cass | Cass County Road Commission | Marcellus Highway | Glenwood to O'Keefe | 1 | Resurface | Resurface | CON |  |  | STL |  | M |  |  | 0 | 120111 |  | 2016-01-20 |  | Exempt | 1/12/16- RTF approved Moved to 2016 on 3/18/2016 |  |  |  |  | 2016-02-11 |  |  |  |  | 4
2019 | Cass | Cass County Road Commission | Dailey Road | from Coulter north 1.0 miles | 1 | Resurface | Resurface | CON |  | 75200 | STL | 18800 | M |  |  | 94000 | 129852 |  | 2016-01-20 |  | Exempt | 1/12/16- RTF approved | 93600 |  |  |  | 2016-02-11 |  |  |  |  | 4
2019 | Cass | Cass County Road Commission | Decatur Road | Crane-Brewer | 2.5 | Restore & rehabilitate | Mill and fill and overlay | CON | ACC | [7 empty] | 123749 |  | 2016-11-21 | Delete | Exempt | I1/12/16- Moved from 2017 to 2019. 2/2/2015- Amending Cost to take into account actual bid amount on project. | 20185 |  |  |  | 2016-12-01 |  |  |  |  | 4
2019 | Van Buren | Village of Breedsville | W Main St | From the West Village Limits to Pine St | 0.5 | Resurface | Crush & Shape West Main Street. During the 2018 construction season, utilizing Local Agency Program funding, crush & shape Main Street from Pine Street westerly to the Village limit (2,700') excluding the railroad crossing. Clean and regrade the ditches, replace driveway culverts and their driveways. Replace defective storm sewer and culvert road crossings. | CON |  | 298560 | STL |  |  | 74640 | VLG | 373200 | 129854 |  | 2016-01-20 |  | Exempt | 1/2016- RTF Approved | 373200 |  |  |  | 2016-02-11 |  |  |  |  | 4
2019 | Van Buren | Village of Decatur | S Williams St | Delaware St (M-51) to the South Village Limits | 0.89 | Resurface | Project includes 3" of cold milling and resurfacing with HMA and geosynthetic paving fabric on S. Williams from the South Village Limits to Delaware St. (M-51) a length of approx. 4,700 ft. ADA compliant ramps would be installed at M-51, Sherwood St. and Beers St. All pavement markings on S. Williams St. would be replaced with recessed pavement markings. | CON |  | 259800 | STL | 61000 | M | 80200 | VLG | 401000 | 129853 |  | 2016-01-20 |  | Exempt | 1/2016- RTF Approved | 401000 |  |  |  | 2016-02-11 |  |  |  |  | 4
2019 | Van Buren | Village of Lawrence | W St. Joseph St | S Paw Paw St to West Village Limits | 0.76 | Resurface | HMA overlay of existing roadway, shoulder additions, sidewalk replacement and additions, ADA ramps | CON | ACC |  |  |  | M |  |  | 0 | 129846 |  | 2017-01-05 | Delete | Exempt | 1/5/17 - State D funds do not AC/ACC. 1/2016- RTF Approved; ACC of 2018 job | 47013 |  |  |  | 2016-02-11 |  |  |  |  | 4
2020 | Berrien | Berrien County Road Commission | Red Arrow Highway | 1.6 miles South of the City limits of Bridgman to 2.4 miles South of Bridgman | 0.8 | Resurface | 3R Project | CON |  | 646233 | STL | 117363 | M | 44195 | CNTY | 807791 | 129836 |  | 2016-10-07 | Cost | Exempt | 10/7/2016 - Cost and scope have changed. 1/20/16- RTF approved | 807791 |  |  |  | 2016-10-12 |  |  |  |  | 4
2020 | Cass | Cass County Road Commission | Pavement Marking | Pavement marking |  | Traffic ops/safety | Pavement Marking centerline and edgeline on selected roads | CON |  | 75000 | STL |  |  |  |  | 75000 | 129855 |  | 2016-01-20 |  | Exempt | 1/12/16- RTF 4 Approved | 75000 |  |  |  | 2016-02-11 |  |  |  |  | 4
2020 | Cass | Cass County Road Commission | Dailey Road | M60 southwards 0.8 miles | 0.8 | Resurface | Resurface | CON |  | 75200 | STL | 18880 | M |  |  | 94080 | 129857 |  | 2016-01-20 |  | Exempt | 1/20/16- RTF approved | 93600 |  |  |  | 2016-02-11 |  |  |  |  | 4
2020 | Cass | Cass County Road Commission | Marcellus Highway | Twin Lakes to Glenwood | 1.09 | Resurface | Resurface | CON |  |  | STL |  | M |  |  |  | 120109 |  | 2016-01-20 |  | Exempt | 1/20/16- RTF approved Moved to 2016 March 18 |  |  |  |  | 2016-02-11 |  |  |  |  | 4
2020 | Cass | Cass County Road Commission | Dutch Settlement Road | Goff to Savage | 0.94 | Resurface | Resurface | CON |  | 75200 | STL | 18800 | M |  |  | 94000 | 129858 |  | 2016-01-20 |  | Exempt | 1/20/2016- RTF approved |  |  |  |  | 2016-02-11 |  |  |  |  | 4
2020 | Cass | Cass County Road Commission | Cassopolis Road | Bullhand to Calvin Hill | 1 | Resurface | Resurface | CON |  | 75200 | STL | 18800 | M |  |  | 94000 | 129856 |  | 2016-01-20 |  | Exempt | 1/20/16- RTF approved | 93600 |  |  |  | 2016-02-11 |  |  |  |  | 4
2020 | Van Buren | Van Buren County Road Commission | Red Arrow Highway | 26th to 28th St | 1.1 | Resurface | Trench and widen to accommodate 3-lane section with paved shoulders. Involves milling off existing HMA approx. 2 inches, installing fabric, repaving. Minor drainage improvements, tree removals and trimming and all other associated work. | CON |  | 556887 | STL | 108113 | M | 285000 | CNTY | 950000 | 129837 |  | 2016-01-20 |  | Exempt | 1/2016- RTF Approved; Is in KATS LRP and is being coordinated with KATS funds. |  |  |  |  | 2016-02-11 |  |  |  |  | 4
2021 | Van Buren | Village of Bloomingdale | W Kalamazoo St | Oak Street to West Village Limits | 0.72 | Reconstruct | Replace unsuitable subgrade with 12" of sand subbase and 8" of aggregate base. Replace removed asphalt with 5" of HMA. Place 6" underdrain along both sides of the road to alleviate areas of wet subgrade. Proposed cross-section consists of two (2) 12 foot driving lanes, with 3' paved shoulders on each side. Existing areas of curb & gutter, and sidewalk shall remain, with possible spot repairs as necessary. New ADA sidewalk ramps, with detectable warning surface, shall be constructed at intersections. Driveway approaches shall be replaced with like materials. | CON |  | 521200 | STL |  |  | 130000 | VLG | 651200 | 129859 |  | 2016-01-20 |  | Exempt | 1/2016- RTF Approved . This is an Illustrative List project. PRIORITY 1 for any extra funding that becomes available in Van Buren County from 2017-2020, and will be given first priority in 2021. Village is willing to provide up to $330,000 in local match to get project done, reducing STP request to 321,000. | 651000 |  |  |  | 2016-02-11 |  |  |  |  | 4
1 | Berrien | Berrien County Road Commission | Red Arrow Highway | City of Bridgman limits to 0.8 miles South | 0.8 | Resurface |  | CON |  | 697521 | STL | 131180 | M | 43200 | CNTY | 871901 |  |  | 2016-10-07 |  | Exempt | 10/7/206 moved to the illustrative list 5/26/16 Approved |  |  | Illustrative |  | 2016-05-26
1 | Berrien | Berrien County Road Commission | Hills Road | Village of Baroda limits to Shawnee Road |  | Resurface | Hills Road Resurface | CON |  | 97521 | STL | 131180 | M | 43200 | CNTY | 271901 | 131454 |  | 2016-10-07 |  |  | 10/7/2016 Moved to the Illustrative List |  |  | Illustrative |  | 2016-10-12
1 | Van Buren | City of Gobles | E Van Buren Street | M-40 to 32nd St | 0.84 | Reconstruct | The project includes removing existing pavement, machine grading, 8" aggregate base, 5" hot mix asphalt roadway with concrete curb and gutter, storm sewer, replacement of sidewalk at crosswalks for ADA ramps and restoration | CON |  | 613000 | STL |  |  | 613000 | CITY | 1226000 |  |  | 2016-01-20 |  | Exempt | 1/2016 RTF Approved | 1226000 |  | Illustrative |  | 2016-02-11 |  |  |  |  | 4
1 | Van Buren | City of Gobles | W Van Buren St | W City Limits to M-40 | 0.5 | Reconstruct | The project includes removing existing pavement, machine grading, 8" aggregate base, 5" hot mix asphalt roadway with concrete curb and gutter, storm sewer, replacement of sidewalk at crosswalks for ADA ramps and restoration. | CON |  | 564800 | STL |  |  | 141200 | CITY | 706000 |  |  | 2016-01-20 |  | Exempt | 1/2016 RTF Approved | 706000 |  | Illustrative |  | 2016-02-11 |  |  |  |  | 4
1 | Van Buren | Van Buren County Road Commission | CR 380 | CR 681 to the West Village Limits of Breedsville | 1.5 | Resurface | Trench, widen, crush and shape for reconstruction of entire section, adjust/upgrade guardrail as required, drainage improvements and all associated work. | CON |  | 440000 | STL |  |  | 210000 | CNTY | 650000 |  |  | 2016-01-20 |  | Exempt | 1/2016 RTF Approved. | 650000 |  | Illustrative |  | 2016-02-11 |  |  |  |  | 4
1 | Van Buren | Van Buren County Road Commission | CR 388 | 29th St to CR 653 | 1.5 | Resurface | Trench, widen and overlay entire length, adjust/upgrade guardrail as required, tree removals and trimming, drainage improvements and all associated work. | CON |  | 416887 | STL |  |  | 225000 | CNTY | 641887 |  |  | 2016-01-20 |  | Exempt | 1/2016 RTF Approved. | 642000 |  | Illustrative |  | 2016-02-11 |  |  |  |  | 4
1 | Van Buren | Village of Breedsville | Main Street | Pine St to East Village Limits | 0.5 | Resurface | Crush & Shape East Main Street : During the 2018 construction season, utilizing Local Agency Program funding, crush & shape Main Street from the east end of downtown (500' east of Pine Street) easterly to the Village limit (2,200'). Clean and regrade the ditches, replace driveway culverts and their driveways. Replace defective storm sewer and culvert road crossings. | CON |  | 248000 | STL |  |  | 49600 | VLG | 297600 |  |  | 2016-01-20 |  | Exempt | 1/2016 RTF Approved | 297600 |  | Illustrative |  | 2016-02-11 |  |  |  |  | 4
1 | Van Buren | Village of Breedsville | Pine Street | North Village Limits to Main | 0.4 | Resurface | Crush & Shape from Pine Street from Main Street northerly to the village limit (2,700') Clean and Regrade the ditches, replace driveways culverts and their driveways. Replace defective storm sewer and culvert road crossings. | CON |  | 282000 | STL |  |  | 56400 | VLG | 338400 |  |  | 2016-01-20 |  | Exempt | 1/2016 RTF Approved | 338400 |  | Illustrative |  | 2016-02-11 |  |  |  |  | 4
Verify Data
Paste Values

## RTF Constraint
Berrien County County | [5 empty] | Cass County | [5 empty] | Van Buren County
| 2017 | 2018 | 2019 | 2020 | Total |  | 2017 | 2018 | 2019 | 2020 | Total |  | 2017 | 2018 | 2019 | 2020 | Total
Revenue | [5 empty] | Revenue | [5 empty] | Revenue
Federal STP-Rural | 709167 | 732826 | 747482.52 | 762432.1704 | 2951907.6904 | Federal STP-Rural | 560410 | 579820 | 591416.4 | 603244.728 | 2334891.128 | Federal STP-Rural | 757030 | 783233 | 798897.66 | 814875.6132 | 3154036.2732
State D Allocation | 128256 | 108176 | 117363 | 117363 | 471158 | State D Allocation | 88954 | 75026 | 81398 | 81398 | 326776 | State D Alliocation | 118148 | 99650 | 108113 | 108113 | 434024
Carry over from previous year | 45856 | 173061 | 22468 | 22468 |  | Carry over from previous year | 30813 | 18046 | 45472 | 57310 |  | Carry over from previous year | -75978 | 16170 | 68807 | 115920
Sate D available to spend | 174112 | 281237 | 139831 | 139831 | 517014 | Sate D available to spend | 119767 | 93072 | 126870 | 138708 | 357589 | Stae D avaliable to spend | 42170 | 115820 | 176920 | 224033 | 358046
Local Match | 329548 | 12500 | 56800 | 44195 | 443043 | Local Match | 35425 | 27000 | 0 | 0 | 62425 | Local Revenue | 529530 | 47013 | 154840 | 285000 | 1016383
Total Revenue | 1386939 | 1307800 | 1083944.52 | 1086289.1704 | 4864972.6904 | Total Revenue | 835369 | 792964 | 845156.4 | 880660.728 | 3354150.128 | Total Revenue | 1370900 | 1061886 | 1307577.66 | 1547941.6132 | 5288305.2732
Programed Costs | [5 empty] | Programed Costs | [5 empty] | Programed Costs
Federal Cost | 709167 | 621139 | 633562 | 646233 | 2610101 | Federal Cost | 560410 | 373400 | 353240 | 225400 | 1512450 | Federal Cost | 757030 | 648318 | 558360 | 556887 | 2520595
State Cost | 0 | 258769 | 117363 | 117363 | 493495 | State Cost | 98983 | 47600 | 69560 | 37680 | 253823 | State Cost | 26000 | 47013 | 61000 | 108113 | 242126
Local Cost | 329548 | 12500 | 56800 | 44195 | 443043 | Local Cost | 35425 | 27000 | 0 | 0 | 62425 | Local Cost | 529530 | 47013 | 154840 | 285000 | 1016383
Total Cost | 1038715 | 892408 | 807725 | 807791 | 3546639 | Total Cost | 694818 | 448000 | 422800 | 263080 | 1828698 | Total Cost | 1312560 | 742344 | 774200 | 950000 | 3779104
Federal Balance | 0 | 111687 | 113920.52 | 116199.1704 | 341806.6904 | Federal Balance | 0 | 206420 | 238176.4 | 377844.728 | 822441.128 | Federal Balance | 0 | 134915 | 240537.66 | 257988.6132 | 633441.2732
State Balance | 174112 | 22468 | 22468 | 22468 | 22468 | State Balance | 20784 | 45472 | 57310 | 101028 | 101028 | State Balance | 16170 | 68807 | 115920 | 115920 | 115920
RTF Region IV
| 2017 | 2018 | 2019 | 2020 | Total | Funding allocation for FY 2019 & 2020 are estimates
Revenue
Federal STP-Rural | 2026607 | 2095879 | 2137796.58 | 2180552.5116 | 8440835.0916
State D Allocation | 335358 | 282852 | 306874 | 306874 | 1231958
Carry over from previous year | 691 | 207277 | 136747 | 195698
Sate D available to spend | 336049 | 490129 | 443621 | 502572 | 1232649
Local Match | 894503 | 86513 | 211640 | 329195 | 1521851
Total Revenue | 3593208 | 3162650 | 3236678.58 | 3514891.5116 | 13507428.0916
Programed Costs
Federal Cost | 2026607 | 1642857 | 1545162 | 1428520 | 6643146
State Cost | 124983 | 353382 | 247923 | 263156 | 989444
Local Cost | 894503 | 86513 | 211640 | 329195 | 1521851
Total Cost | 3046093 | 2082752 | 2004725 | 2020871 | 9154441
Federal Balance | 0 | 453022 | 592634.58 | 752032.5116 | 1797689.0916
State Balance | 211066 | 136747 | 195698 | 239416 | 239416

## Codes
Fund Sources
AR | American Recovery and Reinvestment Act - Any Area | Federal
AR1 | American Recovery and Reinvestment Act - 120 Day Obligation | Federal
ARE | American Recovery and Reinvestment Act - Enhancement | Federal
ARE1 | American Recovery and Reinvestment Act - Enhancement - 120 Day Obligation | Federal
ARU | American Recovery and Reinvestment Act - TMA | Federal
ARUL | American Recovery and Reinvestment Act - Small MPO, Small Urban | Federal
ARL | American Recovery and Reinvestment Act - Rural | Federal
AIRR | American Recovery and Reinvestment Act - Indian Reservation Roads | Federal
AFLH | American Recovery and Reinvestment Act - National Park Roads | Federal
AFFH | American Recovery and Reinvestment Act - Forest Highways | Federal
AFBD | American Recovery and Reinvestment Act - Ferry Boats | Federal
BHI | Bridge Rehabilitation - Prior 1991 - Interstate | Federal
BHN | Bridge Rehabilitation - National Highway System (NHS) | Federal
BHO | Bridge Rehabilitation - Not Classified, Off System | Federal
BHT | Bridge Rehabilitation - Surface Transportation Program (STP) | Federal
BI08 | Build Michigan FY08 | Federal
BOWD | Business Opportunity & Workforce Development Center | Federal
BRI | Bridge Replacement - Pre 1991 Interstate | Federal
BRN | Bridge Replacement - National Highway System (NHS) | Federal
BRO | Bridge Replacement - Not Classified, Off System | Federal
BRT | Bridge Replacement - Surface Transportation Program (STP) | Federal
CBCD | Corridor & Border Crossing Discretionary | Federal
CBIP | Coordinated Border Infrastructure Program - SAFETEA-LU | Federal
CM | Congestion Mitigation & Air Quality | Federal
CMG | Congestion Mitigation & Air Quality - 100% Federal | Federal
DIG | ISTEA Demonstration 100% Federal on Interstate | Federal
DOG | ISTEA Demonstration 100% Federal Not Classified | Federal
DPN | ISTEA Demonstration 80% Federal on NHS | Federal
DPO | ISTEA Demonstration 80% Federal Not Classified | Federal
DPS | ISTEA Demonstration 80% Federal on STP | Federal
DPSA | Demonstration Project Section 112 Division A | Federal
DST | Donor Bonus Surface Transportation | Federal
DSTU | Donor Bonus Surface Transportation - (Urban > 200,000) | Federal
DSTT | Donor Bonus Surface Transportation - Rural - Trunkline | Federal
EBSL | Equity Bonus - SAFETEA-LU | Federal
EDAF | Economic Development - Category A with Federal Aid | Federal
EDCF | Economic Development - Category C with Federal Aid | Federal
EDDF | Economic Development - Category D with Federal Aid | Federal
EDFF | Economic Development - Category F with Federal Aid | Federal
ER | Emergency Relief | Federal
FBD | Ferry Boat & Terminal Discretionary | Federal
FFH | Federal Forest Highway | Federal
FLH | Federal Land Highways - Public Lands | Federal
HBOA | Highway Bridge Obligation Authority | Federal
HPP | High Priority Projects (Demo) | Federal
HPSL | High Priority Projects - SAFETEA-LU | Federal
HRRR | High Risk Rural Roads - SAFETEA-LU | Federal
HSG | High Speed Raix Crossings - 100% Federal | Federal
HSIP | Highway Safety Improvement Program - SAFETEA-LU | Federal
IM | Interstate Maintenance - No Added Lanes | Federal
IMD | Interstate Maintenance Discretionary | Federal
IMG | Interstate Maintenance - Safety - 100% Federal | Federal
ITS | Intelligent Transportation Systems | Federal
JST | 85% Minimum Floor Surface Transportation | Federal
JSTU | 85% Minimum Floor Surface Transportation (Urban Area > 200,000) | Federal
LTA | Local Technical Assistance Program | Federal
MG | Minimum Guarantee | Federal
NCII | National Corridor Infrastructure Improvement - SAFETEA-LU | Federal
NH | National Highway System | Federal
NHG | National Highway System - Safety - 100% Federal | Federal
NHI | National Highway Funds on I (Does not Qualify for I) | Federal
NHIM | National Highway Funds on I (Qualifies for IM) | Federal
NHS | National Highway System - MDOT Safety Program | Federal
NRT | National Recreational Trails | Federal
OFHWA | Other FHWA Funds (Specify source in Comments) | Federal
PNRS | Projects of National and Regional Significance | Federal
RP | Research Project | Federal
RPH | American Recovery and Reinvestment Act | Federal
SBD | Scenic Byways - Discretionary | Federal
SIB | State Infrastructure Bank | Federal
SLG | Surface Transportation Safety | Federal
SRSE | Safe Routes to School - Either - SAFETEA-LU | Federal
SRSI | Safe Routes to School - Infrastructure - SAFETEA-LU | Federal
SRSN | Safe Routes to School - Non-infrastructure - SAFETEA-LU | Federal
SST | Supportive Services Training | Federal
ST | Surface Transportation Program (STP) - Any Area | Federal
STE | STP - Enhancement | Federal
STG | STP - Safety - 100% Federal for ST | Federal
STH | STP - Safety - Hazard Elimination | Federal
STI | STP - Interstate (90%) | Federal
STL | STP - Local | Federal
STR | STP - Safety - Rail-Highway Crossing Protection | Federal
STRG | STP - Safety Rail-Highway & Incentive Payment - 100% Federal | Federal
STS | STP - Any Area- MDOT Safety Program | Federal
STT | STP - Trunkline | Federal
STU | STP - Urban Areas > 200,000 Population | Federal
STUL | STP - Urban Areas < 200,000 Population | Federal
STUT | STP - Urban Areas < 200,000 Population - Trunkline | Federal
SUG | STP - Safety - 100% Federal for STU | Federal
TBR | Timber Bridge Fund | Federal
TCP | Tax Compliance Program | Federal
TCSP | Transportation, Community and System Preservation | Federal
TG | Transportation Grant (100% Fed) | Federal
TIP | Transportation Improvements Projects SAFETEA-LU | Federal
3038 | Section 3038 - Over the Road Bus Program | Transit
3045 | Section 3045 - National Fuel Cell Technology Development Program | Transit
5303 | Section 5303 - Metropolitan Transportation Planning | Transit
5304 | Section 5304 - Statewide Transportation Planning | Transit
5305 | Section 5305 - Metropolitan and Statewide Planning | Transit
5307 | Section 5307 - UZA Formula | Transit
5308 | Section 5308 - Clean Fuels Program | Transit
5309 | Section 5309 - Capital Bus and Capital New Starts | Transit
5310 | Section 5310 - Elderly & Disabled | Transit
5311 | Section 5311 - Non-UZA | Transit
5313 | Section 5313 - Transit Cooperative Research Program | Transit
5314 | Section 5314 - National Research and Technology Program | Transit
5316 | Section 5316 - Transit - Section 5316 - Job Access/Reverse Commute | Transit
5317 | Section 5317 - Transit - Section 5317 - New Freedom Initiative | Transit
5320 | Section 5320 - Alternative Transportation in Parks and Public Lands | Transit
5339 | Section 5339 - Alternative Analysis | Transit
5505 | Section 5505 - University Transportation Centers Program | Transit
A307 | Section 5307 - UZA Formula - American Recovery and Reinvestment Act | Transit
A311 | Section 5311 - Non-UZA - American Recovery and Reinvestment Act | Transit
AR-T | American Recovery and Reinvestment Act - Transit | Transit
BI04 | Build Michigan Bond Issue 2004 | State
BI06 | Build Michigan Bond Issue 2006 | State
BI08 | Build Michigan Bond Issue 2008 | State
BT01 | Bond Trunkline Roads for First Issue | State
CTF | Comprehensive Transportation Fund | State
EDA | Economic Development - Category A | State
EDC | Economic Development - Category C | State
EDD | Economic Development - Category D | State
EDF | Economic Development - Category F | State
JT07 | Jobs Today Bond Issue 2007 GARVEE (State AC for Federal GARVEE Bonds) | State
LFMP | Local Fund Match Program - 100% Local | State
M | State Funds - Michigan Betterment | State
MBS | Michigan Budget Stabilization | State
MBWB | Michigan Blue Water Bridge | State
MCS | State Funds - Critical Structures | State
MDA | Drainage Assessment | State
MER | Emergency Program | State
MIR | State Funds - Institutional Roads | State
MRR | Michigan Railroad | State
MRRF | Michigan Revolving Real Estate Fund | State
MS | Safety Program | State
MTB | Turnback Program | State
SIBG | 100% State Infrastructure Bank | State
CITY | Local - City (Specify city in Comments) | Local
CNTY | Local - County (Specify county in Comments) | Local
OLF | Other Local Funds (Specify local fund source in Comments) | Local
PRVT | Private (Non-governmental) | Local
TRAL | Local - Transit Authority Funds (Specify transit authority in Comments) | Local
TWP | Local - Township (Specify township in Comments) | Local
VLG | Local - Village (Specify village in Comments) | Local
Primary Work Types
| Bridge - other | Surface Transportation
| Bridge replacement | Surface Transportation
| Bridge restore & rehabilitate | Surface Transportation
| New route/structure (capacity increase) | Surface Transportation
| Reconstruct | Surface Transportation
| Restore & rehabilitate | Surface Transportation
| Resurface | Surface Transportation
| Roadside facility | Surface Transportation
| Traffic ops/safety | Surface Transportation
| Widen - major (capacity increase) | Surface Transportation
| Widen - minor | Surface Transportation
| Transit communication equipment | Transit
| Transit facility | Transit
| Transit maintenance equipment and parts | Transit
| Transit operations | Transit
| Transit operations equipment | Transit
| Transit vehicle additions/replacements | Transit
| Transit vehicle rehabilitation | Transit
| Aviation | Miscellaneous
| GPA | Miscellaneous
| Heritage routes | Miscellaneous
| Intermodal/multimodal | Miscellaneous
| Marine/port | Miscellaneous
| Miscellaneous | Miscellaneous
| Planning and research | Miscellaneous
| Rail | Miscellaneous
| Studies | Miscellaneous
| Wetland mitigation | Miscellaneous
Amendment Type
Add
Delete
Cost
Scope
Year
Phase
EPE
PE
ROW
CON
T-Cap
T-Ops
SUB
UTL
Local Priority
Illustrative
Verify Data