## Sheet1
Fiscal Year | Job# | County | Responsible Agency | Project Name | Limits | Length | Primary Work Type | Project Description | Phase Status | S/TIP Cycle | Fed Obligated Amount | State Obligated Amount | Local Obligated Amount | Total Obligated Amount | Fed Estimated Amount | State Estimated Amount | Local Estimated Amount | Total Estimated Amount | Cost To Date | Fund Source | Template Name | Action Type | Action Approval Date | Local Fed Approval Date | FHWA Approval Date | FTA Approval Date | Schedule Obligation Date | Actual Obligation Date | Schedule Let Date | Actual Let Date | Federal Amendment Type | Comments | S/TIP Status | RTF | TMA | Small MPO | Small Urban | Flex To FTA Indicator | Total Job Cost | Total Job Cost Incl Non LAP | Project ID | Project Title | Total Project Cost | S/TIP Exempt | Delayed To Future S/TIP Cycle
2022 | 206404 | Berrien | Berrien County | S Red Arrow Hwy | Cherry Beach Road to Sawyer Road, Berrion County | 1.38 | Road Rehabilitation | Milling and two course asphalt resurfacing | Programmed | 20-23 | 0 | 0 | 0 | 0 | 0 | 108176 | 0 | 108176 | 0 | EDD | TEDF Category D | Admin Modification | 2021-11-01 | 2019-01-28 | 09/30/2019 | N/A | 2022-03-01 |  | 2022-03-04 |  |  |  | Approved | 4 - Southwest Michigan Planning Commission [SWMPC] |  |  |  | N/A | 1015000 | 1268750 | N/A | N/A
2022 | 206404 | Berrien | Berrien County | S Red Arrow Hwy | Cherry Beach Road to Sawyer Road, Berrion County | 1.38 | Road Rehabilitation | Milling and two course asphalt resurfacing | Programmed | 20-23 | 0 | 0 | 0 | 0 | 803000 | 0 | 103824 | 906824 | 0 | STL | STP - Rural/Flexible | Admin Modification | 2021-11-01 | 2019-01-28 | 09/30/2019 | N/A | 2022-03-01 |  | 2022-03-04 |  |  |  | Approved | 4 - Southwest Michigan Planning Commission [SWMPC] |  |  |  | N/A | 1015000 | 1268750 | N/A | N/A
2023 | 206408 | Berrien | Berrien County | Red Arrow Hwy | Lakeside Road to Lakeshore Road | 1.449 | Road Rehabilitation | Milling and two coarse asphalt resurfacing | Programmed | 20-23 | 0 | 0 | 0 | 0 | 0 | 108176 | 0 | 108176 | 0 | EDD | TEDF Category D | Admin Modification | 2021-11-01 | 2019-01-28 | 09/30/2019 | N/A | 2023-03-01 |  | 2023-03-03 |  |  |  | Approved | 4 - Southwest Michigan Planning Commission [SWMPC] |  |  |  | N/A | 1032000 | 1290000 | N/A | N/A
2023 | 206408 | Berrien | Berrien County | Red Arrow Hwy | Lakeside Road to Lakeshore Road | 1.449 | Road Rehabilitation | Milling and two coarse asphalt resurfacing | Programmed | 20-23 | 0 | 0 | 0 | 0 | 820000 | 0 | 103824 | 923824 | 0 | STL | STP - Rural/Flexible | Admin Modification | 2021-11-01 | 2019-01-28 | 09/30/2019 | N/A | 2023-03-01 |  | 2023-03-03 |  |  |  | Approved | 4 - Southwest Michigan Planning Commission [SWMPC] |  |  |  | N/A | 1032000 | 1290000 | N/A | N/A
2022 | 207175 | Cass | Cass County | Barron Lake Rd | Barron Lake Road from Cook Street to Pokagon Highway | 2.48 | Road Capital Preventive Maintenance | Mill and one course non-structural overlay | Programmed | 20-23 | 0 | 0 | 0 | 0 | 0 | 87000 | 0 | 87000 | 0 | EDD | TEDF Category D | Admin Modification | 2021-12-16 | 2019-01-28 | 12/13/2019 | N/A | 2022-02-04 |  | 2022-04-01 |  |  |  | Approved | 4 - Southwest Michigan Planning Commission [SWMPC] |  |  |  | N/A | 470000 | 587500 | N/A | N/A
2022 | 207175 | Cass | Cass County | Barron Lake Rd | Barron Lake Road from Cook Street to Pokagon Highway | 2.48 | Road Capital Preventive Maintenance | Mill and one course non-structural overlay | Programmed | 20-23 | 0 | 0 | 0 | 0 | 300623 | 0 | 82377 | 383000 | 0 | STL | STP - Rural/Flexible | Admin Modification | 2021-12-16 | 2019-01-28 | 12/13/2019 | N/A | 2022-02-04 |  | 2022-04-01 |  |  |  | Approved | 4 - Southwest Michigan Planning Commission [SWMPC] |  |  |  | N/A | 470000 | 587500 | N/A | N/A
2022 | 207724 | Cass | Cass County | Rudy Road | Rudy Road over Dowagiac River, Str# 1460, Cass County | 0 | Bridge Replacement | Bridge Replacement | Active | 20-23 | 1008260.408 | 0 | 63016.2755 | 1071276.6835 | 1252800 | 0 | 78300 | 1331100 | 0 | HIPL | HIP - Bridge | Admin Modification | 2021-10-08 | 2019-06-20 | 09/30/2019 | N/A | 2021-10-08 | 2021-10-13 | 2022-01-07 |  |  |  | Approved | 4 - Southwest Michigan Planning Commission [SWMPC] |  |  |  | N/A | 1260325.51 | 1651825.51 | N/A | N/A
2022 | 207177 | Cass | Cassopolis | N O Keefe Rd | North O'Keefe Street from York Street to Graham Street | 0.25 | Reconstruction | Reconstruction | Programmed | 20-23 | 0 | 0 | 0 | 0 | 336377 | 0 | 347377 | 683754 | 0 | STL | STP - Rural/Flexible | Admin Modification | 2021-12-14 | 2019-01-28 | 09/30/2019 | N/A | 2022-01-21 |  | 2022-02-04 |  |  |  | Approved | 4 - Southwest Michigan Planning Commission [SWMPC] |  |  |  | N/A | 915000 | 1087500 | N/A | N/A
2023 | 207179 | Cass | Cass County | Calvin Center Rd | Jeffries Street to Bonnie Street | 0.997 | Road Capital Preventive Maintenance | Mill and one course non-structural overlay | Programmed | 20-23 | 0 | 0 | 0 | 0 | 154880 | 0 | 19360 | 174240 | 0 | STL | STP - Rural/Flexible |  |  | 2019-01-28 | 09/30/2019 | N/A | 2023-02-10 |  | 2023-04-07 |  |  |  | Approved | 4 - Southwest Michigan Planning Commission [SWMPC] |  |  |  | N/A | 193600 | 242000 | N/A | N/A
2023 | 207179 | Cass | Cass County | Calvin Center Rd | Jeffries Street to Bonnie Street | 0.997 | Road Capital Preventive Maintenance | Mill and one course non-structural overlay | Programmed | 20-23 | 0 | 0 | 0 | 0 | 0 | 19360 | 0 | 19360 | 0 | EDD | TEDF Category D |  |  | 2019-01-28 | 09/30/2019 | N/A | 2023-02-10 |  | 2023-04-07 |  |  |  | Approved | 4 - Southwest Michigan Planning Commission [SWMPC] |  |  |  | N/A | 193600 | 242000 | N/A | N/A
2023 | 207181 | Cass | Cass County | Calvin Center Rd | US-12 to Grange Street | 1.32 | Road Capital Preventive Maintenance | Mill and one course non-structural hot-mix-asphalt overlay | Programmed | 20-23 | 0 | 0 | 0 | 0 | 198400 | 0 | 24800 | 223200 | 0 | STL | STP - Rural/Flexible |  |  | 2019-06-25 | 12/13/2019 | N/A | 2023-02-10 |  | 2023-04-07 |  |  |  | Approved | 4 - Southwest Michigan Planning Commission [SWMPC] |  |  |  | N/A | 248000 | 310000 | N/A | N/A
2023 | 207181 | Cass | Cass County | Calvin Center Rd | US-12 to Grange Street | 1.32 | Road Capital Preventive Maintenance | Mill and one course non-structural hot-mix-asphalt overlay | Programmed | 20-23 | 0 | 0 | 0 | 0 | 0 | 24800 | 0 | 24800 | 0 | EDD | TEDF Category D |  |  | 2019-06-25 | 12/13/2019 | N/A | 2023-02-10 |  | 2023-04-07 |  |  |  | Approved | 4 - Southwest Michigan Planning Commission [SWMPC] |  |  |  | N/A | 248000 | 310000 | N/A | N/A
2023 | 207184 | Cass | Cass County | Dailey Rd | Pine Lake Street to Coulter Street | 0.75 | Road Capital Preventive Maintenance | Mill and one course non-structural overlay | Programmed | 20-23 | 0 | 0 | 0 | 0 | 0 | 15650 | 0 | 15650 | 0 | EDD | TEDF Category D | Admin Modification | 2021-11-01 | 2019-01-28 | 09/30/2019 | N/A | 2023-02-10 |  | 2023-04-07 |  |  |  | Approved | 4 - Southwest Michigan Planning Commission [SWMPC] |  |  |  | N/A | 156500 | 195625 | N/A | N/A
2023 | 207184 | Cass | Cass County | Dailey Rd | Pine Lake Street to Coulter Street | 0.75 | Road Capital Preventive Maintenance | Mill and one course non-structural overlay | Programmed | 20-23 | 0 | 0 | 0 | 0 | 125200 | 0 | 15650 | 140850 | 0 | STL | STP - Rural/Flexible | Admin Modification | 2021-11-01 | 2019-01-28 | 09/30/2019 | N/A | 2023-02-10 |  | 2023-04-07 |  |  |  | Approved | 4 - Southwest Michigan Planning Commission [SWMPC] |  |  |  | N/A | 156500 | 195625 | N/A | N/A
2023 | 207345 | Cass | Cass County | County wide | Various | 0 | Traffic Safety | Pavement Markings | Programmed | 20-23 |  |  |  |  | 75000 | 0 | 0 | 75000 | 0 | STL | STP - Rural/Flexible |  |  | 2019-01-28 | 09/30/2019 | N/A | 2023-02-10 |  | 2023-04-07 |  |  |  | Approved | 4 - Southwest Michigan Planning Commission [SWMPC] |  |  |  | N/A | 75000 | 93750 | N/A | N/A
2023 | 207189 | Cass | Cassopolis | Hilton St | North Broadway Street to North O'keefe Street | 0.134 | Reconstruction | Reconstruction | Programmed | 20-23 | 0 | 0 | 0 | 0 | 95520 | 0 | 119923 | 215443 | 0 | STL | STP - Rural/Flexible |  |  | 2019-01-28 | 09/30/2019 | N/A | 2022-12-09 |  | 2023-02-03 |  |  |  | Approved | 4 - Southwest Michigan Planning Commission [SWMPC] |  |  |  | N/A | 230000 | 287500 | N/A | N/A
2023 | 207189 | Cass | Cassopolis | Hilton St | North Broadway Street to North O'keefe Street | 0.134 | Reconstruction | Reconstruction | Programmed | 20-23 | 0 | 0 | 0 | 0 | 0 | 14557 | 0 | 14557 | 0 | EDD | TEDF Category D |  |  | 2019-01-28 | 09/30/2019 | N/A | 2022-12-09 |  | 2023-02-03 |  |  |  | Approved | 4 - Southwest Michigan Planning Commission [SWMPC] |  |  |  | N/A | 230000 | 287500 | N/A | N/A
2022 | 206991 | Van Buren | Breedsville | Pine St | Main Street to North Village Limits | 0.58 | Reconstruction | Reconstruction | Programmed | 20-23 |  |  |  |  | 368000 | 0 | 92400 | 460400 | 0 | STL | STP - Rural/Flexible | Admin Modification | 2021-11-01 | 2019-01-28 | 09/30/2019 | N/A | 2022-01-07 |  | 2022-03-04 |  |  |  | Approved | 4 - Southwest Michigan Planning Commission [SWMPC] |  |  |  | N/A | 460400 | 575500 | N/A | N/A
2022 | 206994 | Van Buren | Decatur | Prairie Ronde St | S. George Street to East Village Limit, Village of Decatur | 0.286 | Reconstruction | Reconstruction | Active | 20-23 |  | 0 | 68447 | 342235 | 253920 | 0 | 63480 | 317400 | 0 | STL | STP - Rural/Flexible | Admin Modification | 2021-11-19 15:23 | 2019-01-28 | 09/30/2019 | N/A | 2021-12-10 | 2021-11-22 | 2022-02-04 |  |  |  | Approved | 4 - Southwest Michigan Planning Commission [SWMPC] |  |  |  | N/A | 342235 | 421585 | N/A | N/A
2022 | 207369 | Van Buren | Lawrence | E Saint Joseph St | South Paw Paw Sreet to East village limits | 0.507 | Road Capital Preventive Maintenance | asphalt overlay. | Programmed | 20-23 | 0 | 0 | 0 | 0 | 0 | 72480 | 0 | 72480 | 0 | EDD | TEDF Category D |  |  | 2019-01-28 | 09/30/2019 | N/A | 2022-08-12 |  | 2022-10-07 |  |  |  | Approved | 4 - Southwest Michigan Planning Commission [SWMPC] |  |  |  | N/A | 388200 | 485250 | N/A | N/A
2022 | 207369 | Van Buren | Lawrence | E Saint Joseph St | South Paw Paw Sreet to East village limits | 0.507 | Road Capital Preventive Maintenance | asphalt overlay. | Programmed | 20-23 | 0 | 0 | 0 | 0 | 238080 | 0 | 77640 | 315720 | 0 | STL | STP - Rural/Flexible |  |  | 2019-01-28 | 09/30/2019 | N/A | 2022-08-12 |  | 2022-10-07 |  |  |  | Approved | 4 - Southwest Michigan Planning Commission [SWMPC] |  |  |  | N/A | 388200 | 485250 | N/A | N/A
2022 | 209851 | Van Buren | Van Buren County | 12th Avenue (County Road 384) | 12th Avenue (County Road 384) over Black River Str# 10740- Van Buren County | 0 | Bridge CPM | Miscellaneous Bridge Capital Preventative Maintenance | Programmed | 20-23 |  |  |  |  | 182444 | 0 | 45611 | 228055 | 0 | HIPL | HIP - Bridge | Admin Modification | 2020-04-30 |  |  | N/A | 2022-01-07 |  | 2022-03-04 |  |  |  | Approved | 4 - Southwest Michigan Planning Commission [SWMPC] |  |  |  | N/A | 228055 | 285069 | N/A | N/A
2023 | 206742 | Van Buren | Van Buren County | County Road 388 | County Road 388 from County Road 653 (29th St.) to 26th St. | 1.501 | Road Rehabilitation | Crush and Shape | Programmed | 20-23 | 0 | 0 | 0 | 0 | 877000 | 0 | 786180 | 1663180 | 0 | STL | STP - Rural/Flexible | Adjustment | 2021-09-08 | 2019-01-28 | 09/30/2019 | N/A | 2022-10-07 |  | 2022-12-02 |  |  |  | Approved | 4 - Southwest Michigan Planning Commission [SWMPC] |  |  |  | N/A | 1790000 | 2237500 | N/A | N/A
2023 | 206742 | Van Buren | Van Buren County | County Road 388 | County Road 388 from County Road 653 (29th St.) to 26th St. | 1.501 | Road Rehabilitation | Crush and Shape | Programmed | 20-23 | 0 | 0 | 0 | 0 | 0 | 126820 | 0 | 126820 | 0 | EDD | TEDF Category D | Adjustment | 2021-09-08 | 2019-01-28 | 09/30/2019 | N/A | 2022-10-07 |  | 2022-12-02 |  |  |  | Approved | 4 - Southwest Michigan Planning Commission [SWMPC] |  |  |  | N/A | 1790000 | 2237500 | N/A | N/A
Preferences:
Report Name: All Project Search Report
Run Date: 01/05/2022
Report Type: Standard
FISCAL Year(s): 2022, 2023
MPO/Non-MPO: ALL
County: ALL
Prosperity Region: ALL
MDOT Region: ALL
STIP Cycle: Fiscal Year 2020 - Fiscal Year 2023
STIP Status: Approved, Pending
Job Type: Local, Multi-Modal
Phase Type: ALL
Phase Status: ALL
Amendment Type: ALL
Template: Local - ALL, Multi-Modal - ALL
Finance System: Local - EDD,STL,HIPL, Multi-Modal - STL
RTF: 4 (Berrien,Cass,Van Buren)
Include S/TIP Exempt: No
Include Delayed to Future S/TIP Cycle:No
Note : For Local and Multi-Modal jobs, Total Job Cost and Total Project Cost may include Non LAP Funds
Note:Job Phase(s) highlighted in yellow are delayed to future S/TIP cycle